## Hospital CMMS Gantt
Hospital CMMS - Gantt Chart Devicecare
# | Task / Phase | Category | Duration | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12
1 | System Design (ERD, UI/UX Wireframes) | Planning | 1 week
2 | Backend Setup & Project Initialization | Backend | 1 week
3 | Authentication System (JWT & Roles) | Backend | 1 weeks
4 | User Management APIs | Backend | 1 week
5 | Device Management APIs | Backend | 1 week
6 | Maintenance Request APIs | Backend | 1 week
7 | Request Status Tracking | Backend | 1 week
8 | Frontend Setup | Frontend | 1 week
9 | Login & Authentication Pages | Frontend | 1 week
10 | Dashboard UI | Frontend | 1 week
11 | Create Request Page | Frontend | 1 week
12 | Track Requests Page | Frontend | 1 week
13 | Frontend-Backend Integration | Integration | 1 week
14 | Notification System | Integration | 1 week
15 | Testing & Bug Fixing | Testing | 1 week
16 | Deployment & Final Presentation | Deployment | 1 week
17
Milestones
Week 2 | System Design Complete
Week 4 | Authentication Complete
Week 6 | Backend Development Complete
Week 10 | Integration Complete
Week 12 | Final Deployment & Presentation